## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Set up the project environment, including JDK, Spring Boot, and MySQL configuration. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S1 | S1 | US -02 | Implement task management CRUD functionality using a Thymeleaf-based user interface. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S1 | S1 | US-03 | Integrate the application with the MySQL database for persistent data storage. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S1 | S1 | US-04 | Implement task filtering, sorting, and pagination in the user interface. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S2 | S2 | US-01 | Introduce status and priority enums and enhance the user interface accordingly. | SHOULD HAVE |  | Dakarai Mahisa | 3- Completed
S2 | S2 | US-02 | Develop RESTful APIs to support task CRUD operations. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S2 | S2 | US-03 | Extend REST APIs to support filtering, sorting, and pagination. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S2 | S2 | US-04 | Validate and test all API endpoints using Postman. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S3 | S3 | US-01 | Implement user registration using email and password with secure data storage. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S3 | S3 | US-02 | Enable account activation through email-based OTP verification. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S3 | S3 | US-03 | Implement user login with credential validation. | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S3 | S3 | US-04 | Enforce authenticated session management to restrict task access to authorized users. | SHOULD HAVE |  | Dakarai Mahisa | 3- Completed
S4 | S4 | US-01 | Implement Reminder Engine for Pending Tasks | SHOULD HAVE |  | Dakarai Mahisa | 3- Completed
S4 | S4 | US-02 | Implement Password Encryption | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S4 | S4 | US-03 | Create User Profile Management | MUST HAVE |  | Dakarai Mahisa | 3- Completed
S4 | S4 | US-04 | Create Export Tasks to CSV feature | SHOULD HAVE |  | Dakarai Mahisa | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | n | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Create Spring Boot project with required dependencies | 2025-11-28 | 2025-11-28 |  | Build | 3- Completed | 0.5
US-01 | T-02 | Configure JDK, application properties, and profiles | 2025-11-29 | 2025-11-29 |  | Others | 3- Completed | 1
US-02 | T-01 | Design task entity and data model | 2025-11-29 | 2025-12-01 |  | Design | 3- Completed | 2
US-02 | T-02 | Implement repository and service layers and create Thymeleaf pages for task CRUD | 2025-12-01 | 2025-12-02 |  | Coding | 3- Completed | 5
US-03 | T-01 | Configure JPA and Hibernate and implement database persistence for tasks | 2025-12-03 | 2025-12-04 |  | Coding | 3- Completed | 4
US-03 | T-02 | Validate CRUD operations with database | 2025-12-04 | 2025-12-05 |  | Others | 3- Completed | 4
US-04 | T-01 | Implement pagination using Pageable | 2025-12-06 | 2025-12-08 |  | Coding | 3- Completed | 3
US-04 | T-02 | Add filtering by status, priority, and title and Validate UI behavior | 2025-12-08 | 2025-12-10 |  | Coding | 3- Completed | 3
SPRINT 2 BACKLOG
US-01 | T-01 | Define status and priority enums | 2025-12-11 | 2025-12-12 |  | Coding | 3- Completed | 1
US-01 | T-02 | Update task entity to use enums | 2025-12-11 | 2025-12-12 |  | Coding | 3- Completed | 1
US-02 | T-01 | Design REST API contract | 2025-12-13 | 2025-12-15 |  | Design | 3- Completed | 3
US-02 | T-02 | Implement CRUD REST endpoints | 2025-12-15 | 2025-12-16 |  | Coding | 3- Completed | 3
US-03 | T-01 | Add pageable repository support | 2025-12-16 | 2025-12-17 |  | Coding | 3- Completed | 2
US-03 | T-02 | Implement filter criteria and sorting options | 2025-12-17 | 2025-12-19 |  | Coding | 3- Completed | 2
US-04 | T-01 | Create Postman collection | 2025-12-20 | 2025-12-22 |  | System Test | 3- Completed | 3
US-04 | T-02 | Test CRUD APIs | 2025-12-22 | 2025-12-24 |  | System Test | 3- Completed | 2
SPRINT 3 BACKLOG
US-01 | T-01 | Design user entity and registration data model | 2025-12-26 | 2025-12-27 |  | Design | 3- Completed | 3
US-01 | T-02 | Create User entity and repository | 2025-12-29 | 2025-12-30 |  | Design | 3- Completed | 3
US-02 | T-01 | Design OTP generation and validation flow | 2026-01-02 | 2026-01-03 |  | Design | 3- Completed | 4
US-02 | T-02 | Implement OTP generation logic | 2026-01-03 | 2026-01-03 |  | Coding | 3- Completed | 2
US-03 | T-01 | Design login authentication flow | 2026-01-05 | 2026-01-06 |  | Design | 3- Completed | 2
US-03 | T-02 | Implement login API / controller | 2026-01-06 | 2026-01-07 |  | Coding | 3- Completed | 2
US-04 | T-01 | Configure Spring Security for session-based authentication | 2026-01-07 | 2026-01-08 |  | Coding | 3- Completed | 1
US-04 | T-02 | Restrict task APIs to authenticated users | 2026-01-08 | 2026-01-09 |  | Coding | 3- Completed | 2
SPRINT 4 BACKLOG
US-01 | T-01 | Design reminder logic for near-due and overdue tasks | 2026-01-09 | 2026-01-10 |  | Design | 3- Completed | 4
US-01 | T-02 | Implement reminder engine and notification trigger | 2026-01-12 | 2026-01-12 |  | Coding | 3- Completed | 5
US-02 | T-01 | Integrate BCrypt password encryption | 2026-01-12 | 2026-01-13 |  | Coding | 3- Completed | 1
US-02 | T-02 | Validate encrypted password during authentication | 2026-01-13 | 2026-01-14 |  | Coding | 3- Completed | 1
US-03 | T-01 | Design user profile entity and data model | 2026-01-15 | 2026-01-16 |  | Design | 3- Completed | 2
US-03 | T-02 | Implement profile creation and update functionality | 2026-01-16 | 2026-01-17 |  | Coding | 3- Completed | 5
US-04 | T-01 | Design CSV export structure for task data | 2026-01-19 | 2026-01-20 |  | Design | 3- Completed | 2
US-04 | T-02 | Implement CSV file generation and download API | 2026-01-21 | 2026-01-22 |  | Coding | 3- Completed | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7